# Proposal — D3Tech Consulting

SUMMIT ANALYTICS

Prepared For: D3Tech Consulting

Prepared By: Summit Analytics

Date: July 8, 2026

Contact: Maya Chen

Proposal Type: Cloud Migration

Style: Executive

Confidential — Prepared by Summit Analytics

# Cloud Migration Proposal for D3Tech Consulting

Prepared for:* D3Tech Consulting

Prepared by:* Summit Analytics

Date:* July 8, 2026

Investment:* USD 48,000

Timeline:* 10 weeks

Valid until:* August 31, 2026

## Executive Summary

D3Tech Consulting operates three regional operations hubs on a legacy on-premises stack that slows inventory and order access, complicates backups, and limits remote operations support. Summit Analytics proposes a controlled migration of core operations and administrative workloads to a hardened cloud environment, with downtime windows agreed in advance and a clear rollback plan for each phase.

This engagement delivers a production-ready landing zone, migrated application tiers, validated backups, and an operations handbook your team can run independently after handoff.

## Understanding Your Challenge

Operations staff report 15-40 second delays opening inventory and order records during peak hours. Nightly backups routinely overrun the maintenance window. Remote leads cannot reliably access the same tooling available on-site. Leadership needs a path that reduces operational risk without disrupting fulfillment SLAs.

## Proposed Solution

Summit Analytics will design and execute a phased migration:

1. Foundation - secure cloud landing zone, identity, networking, and logging baselines

2. Pilot - migrate one non-production hub environment and validate performance

3. Production cutover - migrate remaining hub workloads in scheduled windows

4. Stabilize - tuning, runbooks, and knowledge transfer

Commercial terms in this proposal are confirmed: USD 48,000 fixed fee over 10 weeks. Capacity and ROI figures marked as estimates are for planning only and will be refined during discovery week one.

## Deliverables

Cloud landing zone with network segmentation and baseline security controls

Migrated application and database tiers for three operations hubs

Documented cutover and rollback procedures

Backup and restore validation report

Operations runbook and 2× knowledge-transfer workshops

30-day hypercare window after production cutover

## Investment

| Item | Amount |
| --- | --- |
| Discovery & architecture | USD 8,000 |
| Landing zone & security baseline | USD 12,000 |
| Migration & cutover | USD 20,000 |
| Stabilization & knowledge transfer | USD 8,000 |
| Total (fixed) | USD 48,000 |

Payment schedule: 40% on kickoff, 40% at production cutover, 20% at hypercare close.

## Timeline

| Phase | Duration | Outcome |
| --- | --- | --- |
| Discovery & design | Weeks 1-2 | Architecture approved |
| Landing zone | Weeks 3-4 | Environment ready |
| Pilot migration | Weeks 5-6 | Pilot validated |
| Production cutover | Weeks 7-8 | Hubs live |
| Stabilize & handoff | Weeks 9-10 | Runbooks delivered |

## Next Steps

1. Confirm stakeholder availability for a 90-minute kickoff.

2. Provide current inventory of applications, databases, and identity providers.

3. Sign this proposal by August 31, 2026 to lock the fixed fee and schedule.

4. Schedule discovery workshops for the week of September 8, 2026.

## Email Draft

Subject: D3Tech Consulting - Cloud Migration Proposal from Summit Analytics Dear Alex Rivera, Thank you for the time your team shared during discovery. Attached is Summit Analytics' proposal to migrate D3Tech Consulting's hub workloads to a secure cloud environment over a 10-week fixed engagement at USD 48,000. We are ready to begin the week of September 8, pending your approval. Please let us know a convenient time to walk through the plan with your operations and IT leads. Best regards, Maya Chen Summit Analytics maya.chen@summit-analytics.example - 1 (628) 555-0194

# Thank You

We appreciate the opportunity to partner with you.

Summit Analytics

Maya Chen

maya.chen@summit-analytics.example

+1 (628) 555-0194